## Dashboard
Valaiyagam E-Commerce — Project Tracking Dashboard
Project | Valaiyagam Commerce Admin + Storefront
Start Date | 2026-07-14
Planned End | 2026-11-01
Document Date | 2026-07-19
KPI | Value
Total Stories | 32
Done | 9
Planned | 23
% Complete | 28.12%
How to use this workbook
1. Update Stories sheet status weekly (Done / In Progress / Planned / Blocked).
2. Create Git branch using the exact name in column Git Feature / Branch.
3. Link PRs to Story ID (example: VL-019) in the PR title.
4. Review Timeline sheet in client weekly calls.
5. Use Workflow sheet as Definition of Done checklist.
6. Track payment/courier/tracking readiness on Integrations sheet.
Related docs
docs/ECOM_ARCHITECTURE_AND_TIMELINE.md
docs/Valaiyagam_Client_Presentation.pptx

## Stories
ID | Date | Phase | Week | Module | Story Title | User Story | Git Feature / Branch | Branch Type | Priority | Status | Owner | Estimate (Days) | Depends On | Acceptance Criteria | Notes
VL-001 | 2026-07-13 | P0 Foundation | 1 | Platform | Project bootstrap & Docker network | As a developer, I can run the full stack with docker compose so local setup is consistent. | feat/platform-docker-compose | feat | P0 | Done | Backend | 2 | - | Compose brings up mysql, backend, frontend on shared network | valaiyagam-network live
VL-002 | 2026-07-13 | P0 Foundation | 1 | Backend | Layered FastAPI structure | As a developer, I have model/schema/repository/service/route layers for maintainable APIs. | feat/backend-layered-structure | feat | P0 | Done | Backend | 2 | VL-001 | Folders and imports follow agreed architecture | Aligned with client architecture doc
VL-003 | 2026-07-13 | P0 Foundation | 1 | Auth | JWT login + Argon2 passwords | As an admin, I can securely sign in and receive an access token. | feat/auth-jwt-login | feat | P0 | Done | Backend | 2 | VL-002 | Login returns token; invalid credentials rejected | OAuth2 password form
VL-004 | 2026-07-13 | P0 Foundation | 1 | RBAC | Default roles seed (admin/manager/viewer) | As the system, I seed default roles and an initial admin user on first boot. | feat/rbac-default-roles-seed | feat | P0 | Done | Backend | 1 | VL-003 | admin/manager/viewer exist; initial admin can login | Credentials via env
VL-005 | 2026-07-20 | P0 Foundation | 2 | Users | User CRUD APIs | As an admin, I can create, list, update, and delete users with role assignment. | feat/users-crud-api | feat | P0 | Done | Backend | 2 | VL-004 | All CRUD endpoints work with RBAC guards | Admin-only write
VL-006 | 2026-07-20 | P0 Foundation | 2 | Roles | Role CRUD APIs | As an admin, I can manage custom roles while system roles stay protected. | feat/roles-crud-api | feat | P0 | Done | Backend | 1 | VL-004 | Cannot delete/rename protected roles unsafely | Name update supported
VL-007 | 2026-07-20 | P0 Foundation | 2 | Frontend | Light glass admin shell + Redux store | As an admin, I use a light glassmorphism UI with Redux-managed auth/users/roles. | feat/admin-glass-ui-redux | feat | P0 | Done | Frontend | 3 | VL-005 | Login + dashboard match UI standards | No dark theme
VL-008 | 2026-07-20 | P0 Foundation | 2 | Frontend | User/Role edit modals + confirm delete | As an admin, I can edit users/roles in modals and must confirm deletes. | feat/admin-edit-confirm-modals | feat | P0 | Done | Frontend | 2 | VL-007 | Edit works; delete uses ConfirmDialog | Mobile responsive cards
VL-009 | 2026-07-20 | P0 Foundation | 2 | Database | MySQL schema + Alembic initial migration | As a developer, schema changes are versioned with Alembic and SQL init scripts. | feat/alembic-initial-schema | feat | P0 | Done | Backend | 2 | VL-002 | alembic upgrade head creates users/roles/user_roles | 002_schema.sql added
VL-010 | 2026-07-27 | P1 Catalog | 3 | Catalog | Category CRUD | As an admin, I can create and organize product categories. | feat/catalog-categories | feat | P1 | Planned | Backend | 3 | VL-009 | Nested or flat categories with active flag | Includes admin UI
VL-011 | 2026-07-27 | P1 Catalog | 3 | Catalog | Product create/edit with media | As an admin, I can publish products with images, price, and description. | feat/catalog-products-media | feat | P1 | Planned | Fullstack | 5 | VL-010 | Product visible in admin list; media upload works | S3/local storage TBD
VL-012 | 2026-08-03 | P1 Catalog | 4 | Catalog | Product variants (size/color) | As an admin, I can define variants with SKU and price overrides. | feat/catalog-product-variants | feat | P1 | Planned | Backend | 4 | VL-011 | Variants persist and appear in product detail | -
VL-013 | 2026-08-03 | P1 Catalog | 4 | Inventory | Stock levels & low-stock alerts | As a manager, I can monitor stock and get low-stock warnings. | feat/inventory-stock-alerts | feat | P1 | Planned | Fullstack | 4 | VL-012 | Stock updates on admin; alert threshold configurable | -
VL-014 | 2026-08-10 | P1 Catalog | 5 | Storefront | Public catalog browse & product detail | As a customer, I can browse products and open product details. | feat/storefront-catalog-browse | feat | P1 | Planned | Frontend | 5 | VL-011 | Listing + detail pages responsive | SEO-friendly routes
VL-015 | 2026-08-17 | P2 Orders | 6 | Cart | Cart add/update/remove | As a customer, I can manage cart items before checkout. | feat/cart-management | feat | P1 | Planned | Fullstack | 4 | VL-014 | Guest + logged-in cart supported | -
VL-016 | 2026-08-17 | P2 Orders | 6 | Checkout | Address book & shipping quote | As a customer, I can select delivery address and see shipping estimate. | feat/checkout-address-shipping | feat | P1 | Planned | Fullstack | 5 | VL-015 | Address validation + quote returned | -
VL-017 | 2026-08-24 | P2 Orders | 7 | Orders | Create order lifecycle APIs | As the system, I create orders with line items and status machine. | feat/orders-lifecycle-api | feat | P0 | Planned | Backend | 5 | VL-016 | Statuses: draft/pending/paid/cancelled supported | -
VL-018 | 2026-08-31 | P2 Orders | 8 | Admin | Admin order list & detail | As an admin, I can view and filter orders with line-item detail. | feat/admin-orders-console | feat | P1 | Planned | Frontend | 4 | VL-017 | Filters by status/date; detail shows totals | Glass UI pattern
VL-019 | 2026-09-07 | P3 Payments | 9 | Payments | Razorpay order + checkout SDK | As a customer, I can pay for an order via Razorpay checkout. | feat/payments-razorpay-checkout | feat | P0 | Planned | Fullstack | 5 | VL-017 | Sandbox payment succeeds and maps to order | No card data stored
VL-020 | 2026-09-07 | P3 Payments | 9 | Payments | Payment webhook + signature verify | As the system, I verify gateway webhooks and update payment status idempotently. | feat/payments-razorpay-webhook | feat | P0 | Planned | Backend | 4 | VL-019 | Invalid signature rejected; duplicate events ignored | payment_events audit
VL-021 | 2026-09-14 | P3 Payments | 10 | Payments | Refunds & COD flow | As an admin, I can refund paid orders; customers can choose COD where allowed. | feat/payments-refunds-cod | feat | P1 | Planned | Fullstack | 4 | VL-020 | Partial/full refund + COD order path verified | -
VL-022 | 2026-09-21 | P4 Courier | 11 | Courier | Courier adapter interface | As a developer, I can plug multiple courier partners behind one service contract. | feat/courier-adapter-interface | feat | P0 | Planned | Backend | 3 | VL-021 | create/cancel/track/label methods defined | Manual adapter included
VL-023 | 2026-09-21 | P4 Courier | 11 | Courier | Shiprocket/Delhivery shipment create | As an ops user, I can create a shipment and receive an AWB for a paid order. | feat/courier-create-shipment-awb | feat | P0 | Planned | Backend | 5 | VL-022 | AWB saved on shipment; label URL available | Needs partner credentials
VL-024 | 2026-09-28 | P4 Courier | 12 | Courier | Label print & pickup scheduling | As warehouse staff, I can print labels and schedule pickups. | feat/courier-labels-pickup | feat | P1 | Planned | Fullstack | 4 | VL-023 | Label downloadable; pickup confirmation stored | -
VL-025 | 2026-10-05 | P5 Tracking | 13 | Tracking | Shipment event ingestion | As the system, I ingest courier webhooks/polls into shipment_events. | feat/tracking-shipment-events | feat | P0 | Planned | Backend | 4 | VL-023 | Timeline events ordered by timestamp | -
VL-026 | 2026-10-05 | P5 Tracking | 13 | Tracking | Customer order tracking page | As a customer, I can track my order with a clear status timeline. | feat/tracking-customer-timeline-ui | feat | P0 | Planned | Frontend | 4 | VL-025 | Shows Placed→Delivered stages with AWB | OTP or login gate
VL-027 | 2026-10-12 | P5 Tracking | 14 | Notify | Order/shipment notifications | As a customer, I receive email/SMS updates for payment and shipment milestones. | feat/notifications-order-shipment | feat | P1 | Planned | Backend | 4 | VL-026 | Templates for paid/shipped/delivered | Provider TBD
VL-028 | 2026-10-12 | P5 Tracking | 14 | Admin | Exception queue & manual override | As ops, I can manage delayed/RTO shipments and log manual overrides. | feat/tracking-exception-queue | feat | P1 | Planned | Fullstack | 3 | VL-025 | Override requires reason; audited | -
VL-029 | 2026-10-19 | P6 Launch | 15 | Reports | Sales & fulfillment dashboard | As a business owner, I can view sales, payment, and delivery KPIs. | feat/reports-sales-fulfillment | feat | P1 | Planned | Fullstack | 4 | VL-021 | Daily/weekly charts and CSV export | -
VL-030 | 2026-10-19 | P6 Launch | 15 | QA | UAT script & bugfix sprint | As the client, I can execute UAT and log defects against stories. | fix/uat-bugfix-pass | fix | P0 | Planned | QA | 5 | VL-027 | Critical bugs closed; UAT sign-off recorded | -
VL-031 | 2026-10-26 | P6 Launch | 16 | Ops | Staging → production cutover | As the team, we deploy production with migrations, secrets, and monitoring. | feat/prod-cutover-checklist | feat | P0 | Planned | DevOps | 3 | VL-030 | HTTPS, backups, smoke tests green | -
VL-032 | 2026-10-26 | P6 Launch | 16 | Docs | Client runbook & training | As the client ops team, I have a runbook for daily admin tasks. | docs/client-ops-runbook | docs | P2 | Planned | PM | 2 | VL-031 | Runbook covers users, orders, refunds, shipments | -

## Timeline
Phase | Week Start | Week End | Focus | Milestone | Exit Criteria | Status
P0 Foundation | 2026-07-13 | 2026-07-26 | Auth, RBAC, Docker, UI shell | M1 Foundation demo | Admin login + user/role CRUD | Done
P1 Catalog | 2026-07-27 | 2026-08-16 | Categories, products, inventory | M2 Catalog demo | Publish products to storefront | Planned
P2 Orders | 2026-08-17 | 2026-09-06 | Cart, checkout, order lifecycle | M3 Checkout demo | Place order end-to-end | Planned
P3 Payments | 2026-09-07 | 2026-09-20 | Gateway, webhooks, refunds, COD | M4 Payment demo | Paid order verified | Planned
P4 Courier | 2026-09-21 | 2026-10-04 | Adapters, AWB, labels, pickup | M5 Courier demo | Shipment created from paid order | Planned
P5 Tracking | 2026-10-05 | 2026-10-18 | Timeline UI + notifications | M6 Tracking demo | Customer can track order | Planned
P6 Launch | 2026-10-19 | 2026-11-01 | Reports, UAT, production cutover | M7 Go-live | Production ready checklist | Planned

## Git Branches
Branch Name | Type | Linked Story ID | Title | Target | Status
feat/platform-docker-compose | feat | VL-001 | Project bootstrap & Docker network | develop | Done
feat/backend-layered-structure | feat | VL-002 | Layered FastAPI structure | develop | Done
feat/auth-jwt-login | feat | VL-003 | JWT login + Argon2 passwords | develop | Done
feat/rbac-default-roles-seed | feat | VL-004 | Default roles seed (admin/manager/viewer) | develop | Done
feat/users-crud-api | feat | VL-005 | User CRUD APIs | develop | Done
feat/roles-crud-api | feat | VL-006 | Role CRUD APIs | develop | Done
feat/admin-glass-ui-redux | feat | VL-007 | Light glass admin shell + Redux store | develop | Done
feat/admin-edit-confirm-modals | feat | VL-008 | User/Role edit modals + confirm delete | develop | Done
feat/alembic-initial-schema | feat | VL-009 | MySQL schema + Alembic initial migration | develop | Done
feat/catalog-categories | feat | VL-010 | Category CRUD | develop | Planned
feat/catalog-products-media | feat | VL-011 | Product create/edit with media | develop | Planned
feat/catalog-product-variants | feat | VL-012 | Product variants (size/color) | develop | Planned
feat/inventory-stock-alerts | feat | VL-013 | Stock levels & low-stock alerts | develop | Planned
feat/storefront-catalog-browse | feat | VL-014 | Public catalog browse & product detail | develop | Planned
feat/cart-management | feat | VL-015 | Cart add/update/remove | develop | Planned
feat/checkout-address-shipping | feat | VL-016 | Address book & shipping quote | develop | Planned
feat/orders-lifecycle-api | feat | VL-017 | Create order lifecycle APIs | develop | Planned
feat/admin-orders-console | feat | VL-018 | Admin order list & detail | develop | Planned
feat/payments-razorpay-checkout | feat | VL-019 | Razorpay order + checkout SDK | develop | Planned
feat/payments-razorpay-webhook | feat | VL-020 | Payment webhook + signature verify | develop | Planned
feat/payments-refunds-cod | feat | VL-021 | Refunds & COD flow | develop | Planned
feat/courier-adapter-interface | feat | VL-022 | Courier adapter interface | develop | Planned
feat/courier-create-shipment-awb | feat | VL-023 | Shiprocket/Delhivery shipment create | develop | Planned
feat/courier-labels-pickup | feat | VL-024 | Label print & pickup scheduling | develop | Planned
feat/tracking-shipment-events | feat | VL-025 | Shipment event ingestion | develop | Planned
feat/tracking-customer-timeline-ui | feat | VL-026 | Customer order tracking page | develop | Planned
feat/notifications-order-shipment | feat | VL-027 | Order/shipment notifications | develop | Planned
feat/tracking-exception-queue | feat | VL-028 | Exception queue & manual override | develop | Planned
feat/reports-sales-fulfillment | feat | VL-029 | Sales & fulfillment dashboard | develop | Planned
fix/uat-bugfix-pass | fix | VL-030 | UAT script & bugfix sprint | develop | Planned
feat/prod-cutover-checklist | feat | VL-031 | Staging → production cutover | develop | Planned
docs/client-ops-runbook | docs | VL-032 | Client runbook & training | develop | Planned

## Workflow
Step | Stage | Owner | Input | Output | Tool / Gate
1 | Story drafted | PM | Client requirement | Story in Stories sheet | PROJECT_TRACKING.xlsx
2 | Branch created | Dev | Story ID + title | feat/fix branch | Git
3 | Implementation | Dev | Acceptance criteria | Code + tests | IDE / Docker
4 | Migration (if schema) | Backend | Model change | Alembic revision | alembic revision
5 | Pull request | Dev | Branch commits | PR to develop | GitHub/GitLab
6 | Code review | Peer | PR | Approved PR | Review checklist
7 | CI / smoke | CI | PR build | Green checks | Docker compose tests
8 | Merge | Maintainer | Approved PR | Updated develop | Protected branch
9 | UAT on staging | Client + QA | Build on staging | Pass/fail notes | Staging URL
10 | Story status update | PM | UAT result | Status=Done | Excel tracker
11 | Release to main | DevOps | Stable develop | Production tag | Release checklist

## Integrations
Integration | Provider Options | Phase | Story IDs | Key Objects | Success Metric
Payments | Razorpay (primary), Stripe (optional), COD | P3 | VL-019, VL-020, VL-021 | payments, payment_events, refunds | Paid order confirmed via verified webhook
Courier | Shiprocket / Delhivery / BlueDart + manual | P4 | VL-022, VL-023, VL-024 | shipments, courier_accounts, labels | AWB created from paid order < 2 minutes
Tracking | Partner webhooks + internal timeline | P5 | VL-025, VL-026, VL-027, VL-028 | shipment_events, notifications | Customer sees live timeline with AWB